## Sheet1
BUGS FROM TESTING FOR STOCK APPLICATION
File Associated | Line number | Who Found it | Who's Code | Date Found | Date Fixed | Resolved? | Who fixed it? | Input | Output | Description | error received from chrome
login.html |  | Russell |  | 2018-02-11 |  | no |  | valid email | valid password | Handle exception if username/email Is not found. | 400() from firebase
individualStockPage.js |  | Russell | JH/RS | 2018-02-01 |  | no |  | 1 day button | bad graph | 1 Day button on D3 graph is returning bad graph, handle if api returns if 0; fix the sizing function with it
individualStockPage.js |  | JH | JH | 2018-02-08 |  | no |  | searching for random company in search bar | no logo | Some logos are not returned to the user. Handle that small missing picture sign is shown on screen
individualStockPage.js |  | JH | JH | 2018-02-05 |  | no |  | searching for random company in search bar | no peers | some companies load peers some do not return peers
individualStockPage.js |  | JH | JH | 2018-02-05 |  | no |  | searching for random company in search bar | no stats | some companies load stats some do not return stats; ie 0 debt or null or undefined
individualStockPage.js |  | JH | JH | 2018-02-12 |  | no |  | add to portfolio button press |  | on button press the div moves and shifts the code, just overlay the div with absolute and z-index